## Requirement_Traceability_Matrix
Requirement NO. | Functional Requirement | Category | Status | Source | Additional comments
req 01 | User can create a task | user functionality | Testing | functional requirment
req 02 | User can edit a task | user functionality | Completed | functional requirment
req 03 | User can delete a task | user functionality | In Progress | functional requirment
req 04 | Tasks can be organized by category or list | user functionality | Completed | functional requirment
req 05 | User can set due dates | user functionality | In Progress | project charter
req 06 | User receives task reminders | user functionality | In Progress | prooject charter
req 07 | Tasks can be given priority levels | user functionality | Completed | functional requirment
req 08 | UI must be user-friendly | core functionality | Testing | Non functional requirment
req 09 | App loads in under 5 seconds | core functionality | In Progress | Non functional requirment
req 10 | Passwords must be stored securely (hashed) | core functionality | Completed | Non functional requirment
req 11 | App must be protected from SQL injection | core functionality | Testing | Non functional requirment
req 12 | Admin can view user accounts | admin functionality | In Progress | project charter
req 13 | Admin can provide feedback to users | admin functionality | Completed | project charter
req 14 | System sends notification before due time | user functionality | In Progress | PMP
req 15 | Tasks persist in database after refresh | core functionality | Completed | PMP
req 16 | Drag-and-drop tasks to reorder | user functionality | In Progress | project charter | Improves task organization
req 17 | Users can log in securely | user functionality | Completed | PMP
req 18 | Users can give feedback on the application | user functionality | Completed | PMP
Note on A1: ====== ID#AAABgZ4IzCY eze3 (2025-04-28 09:36:34) • ID: A unique ID number used to identify the requirement in the requirement traceability log.
Note on B1: ====== ID#AAABgZ4IzCU eze3 (2025-04-28 09:36:34) • Technical Assumptions or Customer Needs: This column should be populated with a description of the technical assumption or customer need linked to the functional requirement.
Note on C1: ====== ID#AAABgZ4IzCQ eze3 (2025-04-28 09:36:34) • Functional Requirement: This column should be populated with a description of the functional requirement.
Note on D1: ====== ID#AAABgZ4IzCI eze3 (2025-04-28 09:36:34) • Status: This column should be populated with the current status of the functional requirement.