## Risk Tracking Template
Risk Register
Date of last review:
ID | Description of Risk | Impact | Risk Reponse | Risk Level | Risk owner | Notes
1 | Prototype 1 might be late | High | Split tasks, set deadlines, and check progress on Jira | High | Mariam Nasr | Team meetings help stay on track
2 | Technical problems when building the app | High | Ask TAs for help, work together to fix bugs | High | Sama Ahmed | Keep notes of bugs and how we fix them
3 | Not enough testing may cause bugs | Medium | Test small and full parts of the app often | Medium | Mina Adel | Use tools like Composer to help with testing
4 | Someone wants new features not in the plan | High | Only add after checking and updating the plan (SRS, SDD) | High | Mariam Nasr | Write down all changes and updates
5 | A team member can't work (sick, busy, etc.) | High | Use shared tools like GitHub and Docs so others can continue the work | High | Sama Ahmed | Each task should have a backup person
6 | Problems happen when putting app online | Medium | Test the app on a test server before going live | Medium | Mina Atef | Use a checklist before final upload
7 | We forget something important from the plan | Medium | Meet every week, write down all project details | Medium | Mariam Nasr | Use a checklist (like the Requirements Matrix)
8 | App is hard to use for users | Medium | Let friends test it early, improve based on what they say | Medium | Mina Atef | Change the design if needed
11
12
13
14
15
16
17
18
19